## Release Backlog
Project : | Project Name
Start Date : | 2006-01-01
Code Freeze Date : | 2006-03-01
Item Description | Notes | Time | Who | In Sprint
Feature 1
Task 1 |  | 8 |  | 1
Task 2 |  | 8 |  | 1
Task 3 |  | 8 |  | 2
Task 4 |  | 8 |  | 2
Task 5 |  | 8 |  | 3
Task 6 |  | 8 |  | 3
Task 7 |  | 8 |  | 3
Task 8 |  | 8 |  | 4
Feature 2
Task 1 |  | 8 |  | 1
Task 2 |  | 8 |  | 1
Task 3 |  | 8 |  | 2
Task 4 |  | 8 |  | 2
Task 5 |  | 8 |  | 3
Task 6 |  | 8 |  | 3
Task 7 |  | 8 |  | 3
Task 8 |  | 8 |  | 4
| Backlog Total | 128
| Sprint 1 | 32
| Sprint 2 | 32
| Sprint 3 | 48
| Sprint 4 | 16
| Sprint 5 | 0
| Sprints Total | 128
| Total Remaining | 0

## Sprint 1
Sprint : | 1
Start Date : | 2006-01-01
Project : | Project Name
Goal
Complete all investigation and design work and deliver documents, ideas and time estimates ready for the next Sprint
[5 empty] | Week 1 | [9 empty] | Week 2 | [9 empty] | Week 3 | [9 empty] | Week 4 | [9 empty] | Week 5
[5 empty] | 2006-01-01 |  | 2006-01-02 |  | 2006-01-03 |  | 2006-01-04 |  | 2006-01-05 |  | 2006-01-08 |  | 2006-01-09 |  | 2006-01-10 |  | 2006-01-11 |  | 2006-01-12 |  | 2006-01-15 |  | 2006-01-16 |  | 2006-01-17 |  | 2006-01-18 |  | 2006-01-19 |  | 2006-01-22 |  | 2006-01-23 |  | 2006-01-24 |  | 2006-01-25 |  | 2006-01-26 |  | 2006-01-29 |  | 2006-01-30 |  | 2006-01-31 |  | 2006-02-01 |  | 2006-02-02
Item Description | Notes | Estimated | Worked | Delta | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L | W | L
Feature 1
Task 1 |  | 8 | 8 | 0 |  | 8 | 2 | 6 | 6 | 2
Task 2 |  | 8 | 8 | 0 |  | 8 | 4 | 4 | 4 | 0
Feature 2
Task 1 |  | 8 | 11 | 3 |  | 8 | 6 | 2 | 5 | 0
Task 2 |  | 8 | 6 | -2 |  | 8 | 1 | 7 | 5 | 0
Totals |  | 32 |  | 1 |  | 32 |  | 19 |  | 2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
13
Estimating Accuracy |  |  |  | 96.88%

## Sprint 1 Impediments
Date | Description | Hours Taken | Raised By | Status | Notes | Impact
2006-01-01 | Build server failed | 2 | P1 | RESOLVED | Hard disk failed, need to add it to MOM and have IT manage it
2006-01-01 | Impediment 1 | 1 | P2 | OPEN
2006-01-01 | Impediment 2 | 4 | P3 | IN PROGRESS
| Total | 7
2006-01-02 | Impediment 1 | 2 | P1 | OPEN
2006-01-02 | Impediment 2 | 2 | P2 | OPEN
2006-01-02 | Impediment 3 | 2 | P3 | OPEN
| Total | 6